## Sheet1
Stage | Equipment | Materials | Quantities | Units | Duration
Construction | Concrete Mixer, Steel Cutter, Vibrators, Building Support, Formwork | Concrete | 0.0004 | tons | 65 Days
|  | Steel | 0.003 | tons
|  | Wood | 0.0005 | sheets
Roofing | Roofing Sheets, Roof Hoist, Ladder, Waterproofing Brushes | Roof Tiles (Optional) | 0.002 | units | 20 Days
|  | Waterproofing Material | 3 | liters
Electrical and Plumbing Work | Drill Machine, Pipe Bender, Wire Cutter, Conduit Cutter | Electrical Cables | 12 | coils | 15 Days
|  | Pipes (PVC , UPVC , CPVC) | 0.3 | meters
|  | Fittings | 0.15 | units
External and Internal Plastering | Trowel, Float, Mortar Mixer, Plumb Bob | Cement | 17 | bags | 20 Days
|  | Sand | 4.39 | KG
|  | Wall Putty | 0.35 | kg
Flooring | Tile Cutter, Leveling Tools, Grout Float, Sanding Machine | Tiles | 1 | NOS | 15 Days
|  | Cement | 0.018 | bags
|  | Sand | 0.00402 | tons
|  | Grout | 5 | kg
Doors and Windows Installation | Screwdriver, Drill Machine, Leveling Instruments, Wood Planer | Frames | 10 | frames | 10 Days
|  | Shutters (Optional) | 16 | NOS
|  | Hinges and Screws | 0.13 | units
Painting and Finishing | Putty Knife, Sandpaper, Paint Brushes, Rollers, Ladders | Putty | 0.2 | kg | 20 Days
|  | Primer | 0.1 | liters
|  | Paint | 0.15 | liters
|  | Varnish | 0.05 | liters
Finishing Touches | Screwdriver, Wrench, Carpentry Tools, Landscape Equipment | Electrical Fixtures | 0.05 | units | 10 Days
|  | Plumbing Fixtures | 0.03 | units
|  | Wood | 0.0014 | tons
Inspection and Final Handover | Inspection Instruments, Cleaning Tools | Cleaning Materials | 0.03 | liters | 5 Days
Total Duration |  |  |  |  | 180 Days (~5.9 months)

## Sheet2
MATERIALS | QUANTITY (TONS)
Steel | 2
Cement | 6
Sand | 7
Soil | 5
Coarse Aggregates ( SMALL,MEDIUM,BIG) | 8
BRICK | 10000(NOS)